## Sheet1
# | Date Reported | Module/Page | Issue/Request | Recommended Action | Priority | Status
1 | Jan 28, 2026 | GIS Apps | New Page for RBIA | Create and integrate RBIA page in GIS module | High | Pending
2 | Jan 28, 2026 | UI General | Minor mouse pointer issue in title | Fix cursor/pointer styling in title header | Low | Fixed
3 | Jan 28, 2026 | Navigation | Reposition Infrastructure Program button | Adjust navigation layout placement | Medium | Fixed
4 | Jan 28, 2026 | Infrastructure Program Form | Remove unnecessary fields | Simplify form fields based on requirements | High | Pending
5 | Jan 28, 2026 | Infrastructure Program | Status field update | Review and confirm correct status display/logic | Medium | Pending
6 | Jan 28, 2026 | Attachments | Only allow Single Attachment | Restrict upload component to 1 file | High | Fixed
7 | Jan 28, 2026 | UI Design | GAA design should show only 2 boxes | Redesign layout into 2 main containers | Medium | Pending
9 | Jan 28, 2026 | Regions List | Remove Region Names from UI | Remove region name labels where unnecessary | Medium | Pending
10 | Jan 28, 2026 | Theme Colors | Blue/white too bright – improve contrast | Adjust theme palette + accessibility contrast | High | Fixed
11 | Jan 28, 2026 | Infrastructure Programs | Add numbering arrangement | Implement numbering/order display | Medium | Pending
12 | Jan 28, 2026 | Search/Filter | Filter must auto-search by year | Convert year filter into live search behavior | High | Pending
13 | Jan 28, 2026 | Search | Make everything in one unified search | Consolidate all search inputs into one bar | High | Pending
14 | Jan 28, 2026 | Filters | Remove filter button entirely | Replace with automatic filtering/search | High | Pending
15 | Jan 28, 2026 | Documents & Studies | Feasibility author should not be user | Replace with actual document author metadata | High | Fixed
16 | Jan 28, 2026 | Documents | Show Published Date from author | Add published date field for feasibility documents | High | Pending
17 | Jan 28, 2026 | UI Spacing | Add padding/spacing improvements | Apply consistent spacing in layout components | Medium | Pending
18 | Jan 28, 2026 | Admin Access | Admin per division can access all | Update role permissions per division scope | High | Pending
19 | Jan 30, 2026 | Feasibility Module | Add Search Bar by Year | Implement year field + filter logic | High | Pending
20 | Jan 30, 2026 | Documentation Section | Redundant text below title | Remove duplicated subtitle/label | Medium | Pending
21 | Jan 30, 2026 | IP - Filter Button | Switch year filter to search filter button | Update button purpose + UI label | Medium | Pending
22 | Jan 30, 2026 | Planning Application Sidebar | Highlight selected menu item | Add active focus styling in sidebar navigation | High | Pending
23 | Jan 30, 2026 | Events Module | Event Name should wrap text properly | Enable multiline wrapping for long event titles | Medium | Pending
24 | Jan 30, 2026 | Color Picker | DPWH must have preset assigned color | Add default DPWH color option | Medium | Pending
25 | Jan 30, 2026 | Navigation | GIS App should be placed above with Home | Reorder menu items | High | Pending
26 | Jan 30, 2026 | Divisions per Region | Add Coordinator field | Extend division model + UI form updates | High | Pending
27 | Jan 30, 2026 | Division Details Page | Show Coordinators in details view | Display coordinator information properly | Medium | Pending